TEST / SYNTHETIC DOCUMENT - FOR COMPARISON ENGINE VALIDATION ONLY

| Our Ref: | PB/OPS/TEST/2026/047 |
| --- | --- |
| Date: | 19 August 2026 |
| To: | The Director, Government Services Unit |
| Subject: | Implementation schedule and settlement arrangements |

Dear Sir/Madam,

We refer to the coordination meeting held on 15 August 2026 concerning the proposed settlement arrangement between Postbank and participating government institutions. Following the discussion, we are pleased to provide the proposed implementation timeline and related control measures.

The pilot phase is expected to commence on 1 September 2026 and will run for fourteen (14) calendar days. During this period, participating offices will submit settlement instructions by 2:00 p.m. on each business day, with confirmation reports issued before close of business.

For the initial pilot, any instruction received after the daily cut-off time will be processed on the next business day without exception. No manual overrides will be permitted during the pilot period.

Proposed Activity Schedule

| Activity | Responsible Party | Original / Revised Timing | Output |
| --- | --- | --- | --- |
| Confirm participating offices | Government Services Unit | 22 August 2026 | Approved contact list |
| Technical connectivity check | Postbank ICT & Institution ICT | 25 August 2026 | Connectivity sign-off |
| User readiness briefing | Postbank Operations | 28 August 2026 | Attendance record |
| Pilot commencement | All participating parties | 1 September 2026 | Live pilot begins |
| Pilot close and review | Joint Operations Team | 15 September 2026 | Evaluation report |

Operational and Control Requirements

All settlement instructions must contain the institution reference number, beneficiary account details, amount, and authorized officer name.

Any single instruction above KES 5,000,000 must be confirmed by telephone before processing.

Daily reconciliation reports will be shared by email with the designated institutional contact.

Supporting documents should be retained by each participating office for at least six months.

Postbank will provide an exception report at the end of the pilot. The report will include unprocessed instructions and rejected items for discussion during the final review meeting.

Illustrative Control Thresholds

| Control | Threshold / Requirement |
| --- | --- |
| Single instruction review | KES 5,000,000 |
| Aggregate daily alert | KES 25,000,000 |
| Late correction window | Not permitted |

Kindly review the proposed arrangements and provide written confirmation by 21 August 2026. Should you require clarification, please contact the undersigned.

Yours faithfully,

A. N. TESTUSER

Manager, Operations

Postbank Test Environment

Document status: Original test version