TEST / SYNTHETIC DOCUMENT - FOR COMPARISON ENGINE VALIDATION ONLY

| Our Ref: | PB/OPS/TEST/2026/047-B |
| --- | --- |
| Date: | 21 August 2026 |
| To: | The Director, Government Services Coordination Unit |
| Subject: | Revised implementation schedule and confirmation of settlement arrangements |

Dear Sir/Madam,

We refer to the coordination meeting held on 17 August 2026 concerning the pilot settlement arrangement between Postbank and participating government institutions. Following the clarifications received from your office, we have revised the proposed implementation timeline and related control measures.

The pilot phase is expected to commence on 7 September 2026 and will run for thirty (30) calendar days. During this period, participating offices will submit settlement instructions by 3:00 p.m. on each business day, with confirmation reports issued no later than 5:00 p.m.

To support exception handling, each participating institution shall nominate one primary and one alternate contact person. Urgent correction requests received within thirty minutes after the cut-off may be reviewed by the designated operations supervisor before the daily settlement file is finalized.

Proposed Activity Schedule

| Activity | Responsible Party | Original / Revised Timing | Output |
| --- | --- | --- | --- |
| Confirm participating offices | Government Services Coordination Unit | 24 August 2026 | Approved contact list |
| Technical connectivity check | Postbank ICT & Institution ICT | 27-28 August 2026 | Connectivity sign-off |
| User readiness briefing | Postbank Operations | 2 September 2026 | Attendance record |
| Pilot commencement | All participating parties | 7 September 2026 | Live pilot begins |
| Mid-pilot review | Joint Operations Team | 21 September 2026 | Issue log and actions |
| Pilot close and review | Joint Operations Team | 6 October 2026 | Evaluation report |

Operational and Control Requirements

All settlement instructions must contain the institution reference number, beneficiary account details, amount, purpose of payment, and authorized officer name.

Any single instruction above KES 3,000,000 must receive a secondary internal approval before processing.

Daily reconciliation reports will be made available through the approved secure channel and shared only with designated institutional contacts.

Supporting documents should be retained by each participating office for at least twelve months in accordance with approved records-management requirements.

Any discrepancy involving an account number, amount, beneficiary name, or settlement date must be escalated before final posting.

Postbank will provide a consolidated exception report every Friday during the pilot. The report will include unprocessed instructions, corrected instructions, rejected items, and outstanding confirmations. Material exceptions must be acknowledged by the receiving institution within one business day.

Illustrative Control Thresholds

| Control | Threshold / Requirement |
| --- | --- |
| Single instruction review | KES 3,000,000 |
| Aggregate daily alert | KES 20,000,000 |
| Late correction window | 30 minutes after cut-off |
| Acknowledgement of material exception | Within 1 business day |

Kindly review the revised arrangements and provide written confirmation by 26 August 2026. Where any provision requires further clarification, please identify the specific section so that the joint team can address it before the readiness briefing.

Yours faithfully,

A. N. TESTUSER

Acting Manager, Operations Coordination

Postbank Test Environment

Document status: Revised test version